## Blad2
Kolom1 | Page | Task | Member | Hours | Deadline | … needs to be done before | Thomas | Nish | Ian | Nnamdi | Mo | Artem | Solomon | Jonathan
1 | All | Different permissions | 1 | 20 | 2019-06-14 | - | 20
2 | Dashboard | Design & realisation | 1 | 8 | 2019-06-21 | - | 8
6 | Incident form | Making functional incident form | 2 | 15 | 2019-06-14 | - |  | 15
7 | Incident form | Add checks | 2 | 15 | 2019-06-21 | 6 |  | 15
17 | Overview | Design | 3 | 8 | 2019-06-14 | - |  |  | 8
18 | Overview | Realisation design | 3 | 15 | 2019-06-19 | 17 |  |  | 15
21 | Other | Write querry to import old data into mysql | 3 | 8 | 2019-06-10 | - |  |  | 8
5 | Incident form | Design & markup | 4 | 20 | 2019-06-14 | - |  |  |  | 20
19 | Overview | Give operators and administrators the ability to resolve/close tickets | 4 | 15 | 2019-06-23 | 18 |  |  |  | 15
14 | Menu | Design & realisation | 5 | 12 | 2019-06-10 | - |  |  |  |  | 12
15 | MyTickets | Design & realisation | 5 | 20 | 2019-06-21 | - |  |  |  |  | 20
3 | FAQ | Design & realisation | 6 | 8 | 2019-06-10 | - | [5 empty] | 8
4 | FAQ | Add functionality to change FAQ | 6 | 10 | 2019-06-14 | 3 | [5 empty] | 10
10 | Licence buying page | Design & realisation | 6 | 8 | 2019-06-21 | - | [5 empty] | 8
13 | Login system | Design & markup | 6 | 8 | 2019-06-19 | - | [5 empty] | 8
11 | Login system | Creating login system | 7 | 15 | 2019-06-10 | - | [6 empty] | 15
12 | Login system | Edit account details | 7 | 10 | 2019-06-16 | 11 | [6 empty] | 10
16 | MyTickets | Give users the ability to edit/delete open tickets | 7 | 10 | 2019-06-21 | - | [6 empty] | 10
8 | Individual ticket page | Design | 8 | 8 | 2019-06-10 | - | [7 empty] | 8
9 | Individual ticket page | Realisation design | 8 | 15 | 2019-06-16 | 8 | [7 empty] | 15
20 | Overview | Search function | 8 | 15 | 2019-06-21 | 18 | [7 empty] | 15
|  |  |  | 263 |  |  | 28 | 30 | 31 | 35 | 32 | 34 | 35 | 38